## Tech
Order | Initiatives | Description | BE Estimation | FTE sprints | APP Estimation | FTE sprints | BE + APP | FTE sprints | Design | Priority | Quarter | Cross Dependency | Comments | Asana
1) Board Goals |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  | Total estimation (BE + APP)
Q1 · #3 | Introduce postpaid top-ups (direct billers) | Let a sender pay a relative's postpaid mobile bill through the IMTU flow, starting with Tigo. IMTU today only recharges prepaid numbers. Postpaid customers in Latin America are a growing share of the base, carry higher bills, and pay monthly, which makes them a natural fit for subscriptions. The FY26 Tigo postpaid work sized the connector side as Large; FY27 completes it and exposes it in the app. The flow changes: the number lookup must recognise a postpaid line, the amount is the open bill (or an open range) instead of a fixed denomination, and confirmation may not be instant. | L | 4 | S | 1 | L |  | S | High | Q1 | K2 connectors team (biller integration), Tigo and other carriers for postpaid APIs, Finance for non-instant settlement. | PM first-pass estimate; to be validated by engineering.
Q1 · #5 | Reduce subscription cancellations | Cut voluntary and accidental cancellations across the in, during and out moments of a subscription. Subscriptions are the highest-quality IMTU revenue and the default-on toggle grew them fast, but the September exec review showed the cancel rate is the open problem: the home subscriptions widget is used mostly as a cancel surface and a share of cancels are buyer's remorse within days of an unintended opt-in. The Asana subtasks frame the work as in, during and out. In: a short remorse window with a one-tap undo. During: pause instead of cancel, and a savings message that shows what the subscription has earned. Out: an exit survey that captures the reason and offers a targeted save. Underneath, the cancel funnel needs clean events so each change can be measured. | M | 2 | L | 4 | L |  | M | High | Q1 | Subly (subscription engine), CRM for the Braze savings attribute, Amplitude taxonomy fixes (DCS-5331 style) for the cancel funnel. | PM first-pass estimate; to be validated by engineering.
Q2 · #7 | Add mobile payments (Apple Pay and Google Pay) | Offer Apple Pay and Google Pay as payment methods for IMTU, eGift and eSIM in the BR calling app. Card entry is the biggest friction in first purchase, and mobile wallets carry a fraud rate near zero (Apple Pay dropped to 0.01% in the fraud team's data). The DCS epic exists but has a single unstarted ticket, and the calling-app wallet spec deferred DCS products. This initiative adds both wallets as payment methods across the three DCS products through IDT Pay: the app collects the wallet token, the backend passes it to the processor, and the payment method is stored for subscriptions where the wallet allows it. | L | 4 | L | 4 | L |  | S | High | Q2 | IDT Pay (tokenisation and processor support), Fraud team (Apple Pay fraud at 0.01%), Apple and Google merchant onboarding. | PM first-pass estimate; to be validated by engineering.
Q2 · #8 | Deploy AI-powered dynamic pricing (offer price and variable fees) | Let the price and the fee of an IMTU offer be set per user and per moment by a pricing model, in both the BR and Boss Money apps. Pricing today is one price and one fee per offer for everyone. The pricing team is building a model that sets the offer price and a variable fee from corridor, carrier, user history and time, and the FY26 spike estimated the DCS side as Small to Medium: the apps already render whatever price the backend returns. DCS's job is the integration and the guardrails: call the pricing service when offers are listed, lock the quoted price for the session, show fee and total transparently at confirmation, and make sure promos and subscriptions renew at the rules the customer agreed to. | M | 2 | S | 1 | M |  | S | High | Q2 | Pricing team and OMTU (pricing model and service), K2 (price and fee fields), Legal for price display rules. | PM first-pass estimate; to be validated by engineering.
Q2 · #12 | Support sponsor calling plans and cross-sell them in the IMTU flow | Let a US sender buy a calling plan for the recipient abroad, offered at the moment they top up that recipient. A sponsor calling plan is paid by the US customer and used by the person abroad to call back. The IMTU flow already holds the recipient and the moment of generosity, so the cross-sell is natural: after a top-up, offer a sponsored plan for the same number. DCS provides the catalogue call, the offer placement in the IMTU success screen and recipient page, and the purchase hand-off; the calling product owns provisioning. | M | 2 | M | 2 | M |  | S | High | Q2 | Calling plans product team (sponsor plan catalogue and provisioning), Engager for offer placement. | PM first-pass estimate; to be validated by engineering.
Q3 · #13 | Introduce bundling capabilities for DTC | A bundling service that lets a customer buy and receive several products in one transaction, with bundle pricing. Every cross-sell initiative so far ends in two transactions: the module offers, the customer pays twice. Bundling is the platform piece that removes that: one cart, one charge, multiple fulfilments (top-up plus eGift, top-up plus eSIM, top-up plus sponsor plan), with the option of a bundle price or discount. It is the largest build of the year, mostly backend: bundle definition, price composition, one payment, orchestration of fulfilments with partial-failure handling, and the refund and reporting rules that follow. The app side is a cart and a combined review screen. | XL | 9 | L | 4 | XL |  | L | High | Q3 | K2 catalogue and order services, IDT Pay (single charge, partial refunds), Finance for revenue split, product teams for bundle definitions. | PM first-pass estimate; to be validated by engineering.
Q3 · #14 | Expand the BR app in ROW markets (Pinless, IMTU and eSIM) | Take the BR calling app international with IMTU and eSIM enabled per market, not just US-origin sales. The BR app sells IMTU and eSIM to US customers. The FY27 board goal is to launch and operate the app in rest-of-world markets (Europe and Canada first) with Pinless, IMTU and eSIM. For DCS this means market-aware catalogues, currencies and taxes, local payment methods through IDT Pay, sender-country rules for fraud and promos, localisation, and store listings. The FY26 Portuguese translation and the market flags in the offer catalogue are the starting point. | L | 4 | L | 4 | L |  | M | High | Q3 | Country launch programme (legal, tax, payments per market), IDT Pay local payment methods, Calling (Pinless) team, K2 offer catalogue per market. | PM first-pass estimate; to be validated by engineering.
Q3 · #15 | Support the RAF program with a fully trackable journey | Instrument and complete the Refer-a-Friend journey from invite to first transaction to reward payout so every step is measurable. The new RAF platform launched in FY26 with a $5 IMTU reward, but attribution is still partial: invites, installs, first purchase and payout live in different systems and the RAF event documentation was a recurring chore. This initiative closes the loop in the DCS products: a referral code or link carried through install and first IMTU, eGift or eSIM purchase, reward issuance visible to both parties, and a single funnel in Amplitude and the data warehouse. The IMTU Request Top-Up and Gifting ideas both need this loop to work. | M | 2 | M | 2 | M |  | S | Medium | Q3 | DTC Core (RAF platform, shipped FY26), CRM for reward messaging, Data team for attribution reporting. | PM first-pass estimate; to be validated by engineering.
Q4 · #18 | Personalised experiences via Engager (ML-driven) | Expand Engager from cards on one rail to personalised home layouts, offers and lifecycle campaigns driven by ML models. With Engager cards live on the MTU home (G3) and the module ranking hook in place (G1), FY27 Q4 turns them into a personalisation layer: the home order of sections, the featured offer, the module's single offer and the Braze lifecycle messages are all chosen per user by models trained on transaction history. DCS provides the placements, the feature events the models need, and the experimentation hooks; Data Science owns the models. | M | 2 | M | 2 | M |  | M | Medium | Q4 | Engager and Data Science teams (ML models and next-best-offer), CRM (Braze), G3 Engager cards as the delivery surface. | PM first-pass estimate; to be validated by engineering.
Q4 · #19 | Promo balances support for the BR Wallet | Make promotional balances earned through Boss products spendable from the Wallet in both apps, across all products including Pinless. Promotions today pay out as product-specific credits: an IMTU discount, an eGift bonus, a RAF airtime reward. The Wallet integration shipped in FY26 made the stored balance a payment method for DCS products. This initiative adds a promo balance type to the Wallet so any campaign can pay a reward once and the customer spends it on any product in either app. Pinless is excluded as a source of promos but included as a place to spend them. It turns scattered incentives into one loyalty currency, which the gamification work then draws on. | L | 4 | M | 2 | L |  | S | Medium | Q4 | BR Wallet team (balance types and ledger), BLS promo engine, Boss Money app team, Finance for promo liability. | PM first-pass estimate; to be validated by engineering.
Q4 · #20 | Support the IVA migration for MTU | Move the MTU credit card purchase and self-service flows from the legacy IVR to the AI virtual agent without losing context. The legacy IVR still sells top-ups by phone and handles balance and order questions. The company-wide IVA programme replaces the IVR with a conversational agent, and MTU is one of the flows to migrate. DCS provides the APIs the agent calls: recipient lookup, offer list, promo eligibility, payment with a stored card, order status, and the ability to carry context (caller identity, recipient, partially completed order) between the agent and the app or an agent hand-off. The DTC Universal API CSA connector is the base. | M | 2 | NA | 0 | M |  | NA | Medium | Q4 | IVA (Intelligent Virtual Agent) programme team, CSA and IVR teams, DTC Universal API (CSA connector shipped FY26). | PM first-pass estimate; to be validated by engineering.
2) Business Goals |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  | Total estimation (BE + APP)
Q1 · #1 | Integrate MTU transaction flow to Terminus | Send every IMTU purchase to Terminus for a fraud decision before the top-up is fulfilled. Terminus is IDT's internal fraud decisioning system. Today IMTU relies on a patchwork of controls (IDT Pay checks, card BIN rules, the br-web block list) and none of them fired during the Egypt and Pakistan burner-account cash-out in August 2026. This initiative wires the IMTU purchase flow into Terminus: the backend maps the transaction, sender and recipient attributes Terminus needs, calls it synchronously inside the order flow, and honours approve, reject and review outcomes before the carrier is charged. The work is backend only and was started in FY26, so FY27 closes it rather than opening it. | M (1 left) | 1 | NA | 0 | M |  | NA | High | Q1 | Terminus team (fraud platform). Carry-over from FY26, backend In Progress. | PM first-pass estimate; to be validated by engineering.
Q1 · #2 | New Channel: roll out the WhatsApp MTU chatbot | Let a customer buy a top-up, pay, and check order status inside WhatsApp, on top of the DTC Universal API built in FY26. The DTC Universal API shipped in FY26 exposes customer, product and order data to external channels, and the WhatsApp team is building the conversational layer. DCS owns the product side: offer lookup by recipient number, promo eligibility, checkout hand-off, order confirmation and status queries. The Felix Pago teardown done in August showed the winning pattern: a prefilled deep link into the chat, the carrier and offer resolved from the recipient number, and checkout in the WhatsApp in-app browser. eGift follows in a later phase once the MTU flow proves the channel. | M | 2 | NA | 0 | M |  | NA | High | Q1 | WhatsApp Business team (chatbot and conversation design), DTC Universal API (shipped FY26), MARCOM for the entry deep link. | PM first-pass estimate; to be validated by engineering.
Q1 · #4 | MTU modular component and cross-selling MTU on Money Transfer | Build the reusable IMTU cross-sell module once and embed it first in the Money Transfer flow. A reusable component that presents one personalised IMTU offer inside another product's purchase flow, starting with Money Transfer in the Boss Money app. The first version keeps the IMTU purchase as a separate transaction, so no unified cart is needed. The module takes a recipient (phone number or contact), resolves the carrier and the single best offer through backend rules and remote config, and hands off to the existing IMTU checkout. Pinless, insurance, calling plans, eGift and eSIM reuse the same module later, which is why it is the first build of the year. | M | 2 | L | 4 | L |  | M | High | Q1 | Boss Money app team (host surface), Engager for offer selection. Spec started in Confluence (Modular IMTU Component). | PM first-pass estimate; to be validated by engineering.
Q1 · #6 | Cross-sell 2.0: Engager cards on the MTU home page | Replace the static Boss Recommends rail on the MTU home with cards served and targeted by Engager. The redesigned MTU home ships a cross-sell rail whose content is static BMK configuration. Engager already decides which offer or message a user should see in other parts of the BR app. This initiative makes the MTU home rail an Engager placement: the backend requests cards for the user and the app renders whatever comes back (eGift, eSIM, calling plan, RAF, a subscription nudge), with impressions and taps reported back so Engager can learn. It is the cheapest path to personalised cross-sell and the prerequisite for the Personalised experiences via Engager board goal in Q4. | S | 1 | M | 2 | M |  | S | Medium | Q1 | Engager team (card content and targeting), BR7 MTU home redesign (shipped FY26). | PM first-pass estimate; to be validated by engineering.
Q2 · #9 | Integrate with the KVouchers platform (IDT vouchers and new flows) | Move eGift onto an IDT voucher that the recipient redeems for a branded card, capturing breakage and improving cash flow and fraud control. Today an eGift purchase issues the branded gift card immediately, so IDT pays the supplier at once and any fraud loss is realised at once. KVouchers issues an IDT voucher first; the recipient redeems it for a specific brand or any brand in the catalogue, and only then is the branded card bought. This delays supplier spend, creates breakage on unredeemed vouchers, gives a consistent branded experience, and adds a fraud checkpoint between purchase and redemption. The platform becomes the foundation of eGift, so the existing purchase flow migrates onto it and the redemption experience is new. | L | 4 | M | 2 | L |  | M | High | Q2 | KVouchers platform team, Finance (breakage accounting), eGift supplier contracts. | PM first-pass estimate; to be validated by engineering.
Q2 · #10 | Cross-selling MTU on Pinless (module) | Embed the IMTU module in the Pinless calling flow so callers to a number are offered a top-up for that number. Pinless calling knows the number the customer just called. That number is the best possible IMTU lead: the caller cares about the person and the carrier is known from the lookup. This initiative places the module built in Q1 on the post-call screen and the recent-calls list of the BR calling app, offering a single relevant top-up for the called number. Because the module already exists, the work is the host integration, the trigger rules and the analytics. | S | 1 | S | 1 | S |  | S | High | Q2 | MTU modular component (G1). Calling (Pinless) product team for the host screens. | PM first-pass estimate; to be validated by engineering.
Q2 · #11 | Fraud: integrate the outsourced eGift security layer | Put a specialised fraud vendor in front of every eGift purchase so more good orders are approved and fewer bad ones are paid for. eGift is the most fraud-exposed DCS product because the goods are instant and resellable, and FY26 controls decline a very high share of attempts, much of it issuer declines that no vendor can convert. The vendor handover done in September set the real go-live for March 2027. DCS's work is the integration: device and behavioural signals collected in the app, the vendor decision consumed in the order flow, review outcomes handled, and the results fed back so the model learns. Together with KVouchers, this moves eGift from 'decline everything risky' to 'approve more, hold the risky ones'. | M | 2 | S | 1 | M |  | NA | Medium | Q2 | Fraud vendor (Accertify, decisioning through IDT Pay), Fraud and Finance teams; vendor go-live planned for March 2027. | PM first-pass estimate; to be validated by engineering.
Q3 · #16 | Request Top-Up (SMS based) | Let a recipient abroad ask a sender for a top-up by SMS, landing the sender in a prefilled purchase flow. Request Top-Up turns the recipient into an acquisition channel. The recipient sends a request from a lightweight web page or by replying to an SMS; the sender receives an SMS with a link that opens the app (or web) with the number, carrier and suggested amount prefilled. Senders who are not BR customers land in onboarding with a RAF credit. The FY26 board carried it as a business spike; FY27 builds it once the RAF loop and the WhatsApp channel exist to amplify it. | M | 2 | M | 2 | M |  | M | Medium | Q3 | MARCOM (landing page and SMS templates), SMS gateway, RAF platform for the referral hook. | PM first-pass estimate; to be validated by engineering.
Q3 · #17 | eSIM location-based improvements | Use the traveller's location and trip context to recommend, activate and top up the right eSIM plan at the right moment. The eSIM funnel converts 2.3% end to end and loses most users at order review, partly because the customer has to know which region plan they need. Location awareness fixes the recommendation: detect the destination from the device locale, trip dates or arrival, propose the matching regional plan, remind the traveller to install before departure, and offer a data top-up when usage is high in-country. It also positions the eSIM product for the ROW expansion, where the customer is the traveller rather than the sender. | S | 1 | M | 2 | M |  | S | Medium | Q3 | eSIM supplier (coverage and usage data), OS location permissions. | PM first-pass estimate; to be validated by engineering.
Q4 · #21 | MTU gamification | A cross-product programme of missions, streaks and surprise rewards that drives repeat purchase and product exploration. FY26 shipped the first mechanics as Braze in-app messages: punch cards and first-purchase promos. FY27 turns them into a programme: missions with visible progress, time-limited offers, occasional surprise games, a monthly calendar and sharing of prizes, each targeted to a customer segment. Mechanics and rewards are decided per product. It sits late in the year deliberately so it can pay rewards into the Wallet promo balance and be targeted by Engager rather than by static segments. | M | 2 | L | 4 | L |  | L | Medium | Q4 | BLS promo engine, Braze in-app messages (FY26 punch cards), Wallet promo balance (B9) for rewards, Loyalty team. | PM first-pass estimate; to be validated by engineering.
Q4 · #22 | Introduce crypto payment checkout | Accept crypto payments for IMTU through Triple-A, settled in fiat, with no crypto custody at IDT. The architecture was defined in July 2026: Triple-A acts as the processor, the customer pays from their own wallet, IDT receives fiat, and IDT Pay gains an adapter so crypto is one more payment method in the order flow. It is a Low priority business goal aimed at a specific segment (crypto-native diaspora in corridors like Nigeria and Venezuela), so it lands in Q4 after the payments work that has broader impact. The Asana subtask to run an education call with Triple-A is the PM entry point. | M | 2 | S | 1 | M |  | S | Low | Q4 | Triple-A (crypto payment processor), IDT Pay adapter, Legal and Compliance, Finance for fiat settlement. | PM first-pass estimate; to be validated by engineering.
3) Tech Debt and company tech goals |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  | Total estimation (BE + APP)
| Company tech goals and tech debt (35% of DCS capacity) | Unit test coverage, service consolidation, transaction-history storage, platform upgrades and the standing company tech goals. Reserved capacity, not scheduled per item. | XL |  | XL |  | XL | [5 empty] | Reserved capacity (35%), the FY26 convention. Not scheduled per item.
TOTAL demand (initiatives only)
Tech reserve (35%)
Raw capacity: 3 BE and 3 App devs x 26 sprints
Capacity left for initiatives (raw minus reserve)
Over (negative) or under capacity
Sizing scale and colours follow the FY26 sheet:
Source board:

## Business
Order | Initiatives | Description | BE Estimation | FTE sprints | BE calendar sprints (2 lanes) | APP Estimation | FTE sprints | App calendar sprints (2 lanes) | BE + APP | FTE sprints | Design | Priority | Quarter | Cross Dependency | Comments | Asana
1) Board Goals |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  |  | Total estimation (BE + APP)
Q1 · #3 | Introduce postpaid top-ups (direct billers) | Let a sender pay a relative's postpaid mobile bill through the IMTU flow, starting with Tigo. IMTU today only recharges prepaid numbers. Postpaid customers in Latin America are a growing share of the base, carry higher bills, and pay monthly, which makes them a natural fit for subscriptions. The FY26 Tigo postpaid work sized the connector side as Large; FY27 completes it and exposes it in the app. The flow changes: the number lookup must recognise a postpaid line, the amount is the open bill (or an open range) instead of a fixed denomination, and confirmation may not be instant. | L | 4 |  | S | 1 |  | L |  | S | High | Q1 | K2 connectors team (biller integration), Tigo and other carriers for postpaid APIs, Finance for non-instant settlement. | PM first-pass estimate; to be validated by engineering.
Q1 · #5 | Reduce subscription cancellations | Cut voluntary and accidental cancellations across the in, during and out moments of a subscription. Subscriptions are the highest-quality IMTU revenue and the default-on toggle grew them fast, but the September exec review showed the cancel rate is the open problem: the home subscriptions widget is used mostly as a cancel surface and a share of cancels are buyer's remorse within days of an unintended opt-in. The Asana subtasks frame the work as in, during and out. In: a short remorse window with a one-tap undo. During: pause instead of cancel, and a savings message that shows what the subscription has earned. Out: an exit survey that captures the reason and offers a targeted save. Underneath, the cancel funnel needs clean events so each change can be measured. | M | 2 |  | L | 4 |  | L |  | M | High | Q1 | Subly (subscription engine), CRM for the Braze savings attribute, Amplitude taxonomy fixes (DCS-5331 style) for the cancel funnel. | PM first-pass estimate; to be validated by engineering.
Q2 · #7 | Add mobile payments (Apple Pay and Google Pay) | Offer Apple Pay and Google Pay as payment methods for IMTU, eGift and eSIM in the BR calling app. Card entry is the biggest friction in first purchase, and mobile wallets carry a fraud rate near zero (Apple Pay dropped to 0.01% in the fraud team's data). The DCS epic exists but has a single unstarted ticket, and the calling-app wallet spec deferred DCS products. This initiative adds both wallets as payment methods across the three DCS products through IDT Pay: the app collects the wallet token, the backend passes it to the processor, and the payment method is stored for subscriptions where the wallet allows it. | L | 4 |  | L | 4 |  | L |  | S | High | Q2 | IDT Pay (tokenisation and processor support), Fraud team (Apple Pay fraud at 0.01%), Apple and Google merchant onboarding. | PM first-pass estimate; to be validated by engineering.
Q2 · #8 | Deploy AI-powered dynamic pricing (offer price and variable fees) | Let the price and the fee of an IMTU offer be set per user and per moment by a pricing model, in both the BR and Boss Money apps. Pricing today is one price and one fee per offer for everyone. The pricing team is building a model that sets the offer price and a variable fee from corridor, carrier, user history and time, and the FY26 spike estimated the DCS side as Small to Medium: the apps already render whatever price the backend returns. DCS's job is the integration and the guardrails: call the pricing service when offers are listed, lock the quoted price for the session, show fee and total transparently at confirmation, and make sure promos and subscriptions renew at the rules the customer agreed to. | M | 2 |  | S | 1 |  | M |  | S | High | Q2 | Pricing team and OMTU (pricing model and service), K2 (price and fee fields), Legal for price display rules. | PM first-pass estimate; to be validated by engineering.
Q2 · #12 | Support sponsor calling plans and cross-sell them in the IMTU flow | Let a US sender buy a calling plan for the recipient abroad, offered at the moment they top up that recipient. A sponsor calling plan is paid by the US customer and used by the person abroad to call back. The IMTU flow already holds the recipient and the moment of generosity, so the cross-sell is natural: after a top-up, offer a sponsored plan for the same number. DCS provides the catalogue call, the offer placement in the IMTU success screen and recipient page, and the purchase hand-off; the calling product owns provisioning. | M | 2 |  | M | 2 |  | M |  | S | High | Q2 | Calling plans product team (sponsor plan catalogue and provisioning), Engager for offer placement. | PM first-pass estimate; to be validated by engineering.
Q3 · #13 | Introduce bundling capabilities for DTC | A bundling service that lets a customer buy and receive several products in one transaction, with bundle pricing. Every cross-sell initiative so far ends in two transactions: the module offers, the customer pays twice. Bundling is the platform piece that removes that: one cart, one charge, multiple fulfilments (top-up plus eGift, top-up plus eSIM, top-up plus sponsor plan), with the option of a bundle price or discount. It is the largest build of the year, mostly backend: bundle definition, price composition, one payment, orchestration of fulfilments with partial-failure handling, and the refund and reporting rules that follow. The app side is a cart and a combined review screen. | XL | 9 |  | L | 4 |  | XL |  | L | High | Q3 | K2 catalogue and order services, IDT Pay (single charge, partial refunds), Finance for revenue split, product teams for bundle definitions. | PM first-pass estimate; to be validated by engineering.
Q3 · #14 | Expand the BR app in ROW markets (Pinless, IMTU and eSIM) | Take the BR calling app international with IMTU and eSIM enabled per market, not just US-origin sales. The BR app sells IMTU and eSIM to US customers. The FY27 board goal is to launch and operate the app in rest-of-world markets (Europe and Canada first) with Pinless, IMTU and eSIM. For DCS this means market-aware catalogues, currencies and taxes, local payment methods through IDT Pay, sender-country rules for fraud and promos, localisation, and store listings. The FY26 Portuguese translation and the market flags in the offer catalogue are the starting point. | L | 4 |  | L | 4 |  | L |  | M | High | Q3 | Country launch programme (legal, tax, payments per market), IDT Pay local payment methods, Calling (Pinless) team, K2 offer catalogue per market. | PM first-pass estimate; to be validated by engineering.
Q3 · #15 | Support the RAF program with a fully trackable journey | Instrument and complete the Refer-a-Friend journey from invite to first transaction to reward payout so every step is measurable. The new RAF platform launched in FY26 with a $5 IMTU reward, but attribution is still partial: invites, installs, first purchase and payout live in different systems and the RAF event documentation was a recurring chore. This initiative closes the loop in the DCS products: a referral code or link carried through install and first IMTU, eGift or eSIM purchase, reward issuance visible to both parties, and a single funnel in Amplitude and the data warehouse. The IMTU Request Top-Up and Gifting ideas both need this loop to work. | M | 2 |  | M | 2 |  | M |  | S | Medium | Q3 | DTC Core (RAF platform, shipped FY26), CRM for reward messaging, Data team for attribution reporting. | PM first-pass estimate; to be validated by engineering.
Q4 · #18 | Personalised experiences via Engager (ML-driven) | Expand Engager from cards on one rail to personalised home layouts, offers and lifecycle campaigns driven by ML models. With Engager cards live on the MTU home (G3) and the module ranking hook in place (G1), FY27 Q4 turns them into a personalisation layer: the home order of sections, the featured offer, the module's single offer and the Braze lifecycle messages are all chosen per user by models trained on transaction history. DCS provides the placements, the feature events the models need, and the experimentation hooks; Data Science owns the models. | M | 2 |  | M | 2 |  | M |  | M | Medium | Q4 | Engager and Data Science teams (ML models and next-best-offer), CRM (Braze), G3 Engager cards as the delivery surface. | PM first-pass estimate; to be validated by engineering.
Q4 · #19 | Promo balances support for the BR Wallet | Make promotional balances earned through Boss products spendable from the Wallet in both apps, across all products including Pinless. Promotions today pay out as product-specific credits: an IMTU discount, an eGift bonus, a RAF airtime reward. The Wallet integration shipped in FY26 made the stored balance a payment method for DCS products. This initiative adds a promo balance type to the Wallet so any campaign can pay a reward once and the customer spends it on any product in either app. Pinless is excluded as a source of promos but included as a place to spend them. It turns scattered incentives into one loyalty currency, which the gamification work then draws on. | L | 4 |  | M | 2 |  | L |  | S | Medium | Q4 | BR Wallet team (balance types and ledger), BLS promo engine, Boss Money app team, Finance for promo liability. | PM first-pass estimate; to be validated by engineering.
Q4 · #20 | Support the IVA migration for MTU | Move the MTU credit card purchase and self-service flows from the legacy IVR to the AI virtual agent without losing context. The legacy IVR still sells top-ups by phone and handles balance and order questions. The company-wide IVA programme replaces the IVR with a conversational agent, and MTU is one of the flows to migrate. DCS provides the APIs the agent calls: recipient lookup, offer list, promo eligibility, payment with a stored card, order status, and the ability to carry context (caller identity, recipient, partially completed order) between the agent and the app or an agent hand-off. The DTC Universal API CSA connector is the base. | M | 2 |  | NA | 0 |  | M |  | NA | Medium | Q4 | IVA (Intelligent Virtual Agent) programme team, CSA and IVR teams, DTC Universal API (CSA connector shipped FY26). | PM first-pass estimate; to be validated by engineering.
2) Business Goals |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  |  | Total estimation (BE + APP)
Q1 · #1 | Integrate MTU transaction flow to Terminus | Send every IMTU purchase to Terminus for a fraud decision before the top-up is fulfilled. Terminus is IDT's internal fraud decisioning system. Today IMTU relies on a patchwork of controls (IDT Pay checks, card BIN rules, the br-web block list) and none of them fired during the Egypt and Pakistan burner-account cash-out in August 2026. This initiative wires the IMTU purchase flow into Terminus: the backend maps the transaction, sender and recipient attributes Terminus needs, calls it synchronously inside the order flow, and honours approve, reject and review outcomes before the carrier is charged. The work is backend only and was started in FY26, so FY27 closes it rather than opening it. | M (1 left) | 1 |  | NA | 0 |  | M |  | NA | High | Q1 | Terminus team (fraud platform). Carry-over from FY26, backend In Progress. | PM first-pass estimate; to be validated by engineering.
Q1 · #2 | New Channel: roll out the WhatsApp MTU chatbot | Let a customer buy a top-up, pay, and check order status inside WhatsApp, on top of the DTC Universal API built in FY26. The DTC Universal API shipped in FY26 exposes customer, product and order data to external channels, and the WhatsApp team is building the conversational layer. DCS owns the product side: offer lookup by recipient number, promo eligibility, checkout hand-off, order confirmation and status queries. The Felix Pago teardown done in August showed the winning pattern: a prefilled deep link into the chat, the carrier and offer resolved from the recipient number, and checkout in the WhatsApp in-app browser. eGift follows in a later phase once the MTU flow proves the channel. | M | 2 |  | NA | 0 |  | M |  | NA | High | Q1 | WhatsApp Business team (chatbot and conversation design), DTC Universal API (shipped FY26), MARCOM for the entry deep link. | PM first-pass estimate; to be validated by engineering.
Q1 · #4 | MTU modular component and cross-selling MTU on Money Transfer | Build the reusable IMTU cross-sell module once and embed it first in the Money Transfer flow. A reusable component that presents one personalised IMTU offer inside another product's purchase flow, starting with Money Transfer in the Boss Money app. The first version keeps the IMTU purchase as a separate transaction, so no unified cart is needed. The module takes a recipient (phone number or contact), resolves the carrier and the single best offer through backend rules and remote config, and hands off to the existing IMTU checkout. Pinless, insurance, calling plans, eGift and eSIM reuse the same module later, which is why it is the first build of the year. | M | 2 |  | L | 4 |  | L |  | M | High | Q1 | Boss Money app team (host surface), Engager for offer selection. Spec started in Confluence (Modular IMTU Component). | PM first-pass estimate; to be validated by engineering.
Q1 · #6 | Cross-sell 2.0: Engager cards on the MTU home page | Replace the static Boss Recommends rail on the MTU home with cards served and targeted by Engager. The redesigned MTU home ships a cross-sell rail whose content is static BMK configuration. Engager already decides which offer or message a user should see in other parts of the BR app. This initiative makes the MTU home rail an Engager placement: the backend requests cards for the user and the app renders whatever comes back (eGift, eSIM, calling plan, RAF, a subscription nudge), with impressions and taps reported back so Engager can learn. It is the cheapest path to personalised cross-sell and the prerequisite for the Personalised experiences via Engager board goal in Q4. | S | 1 |  | M | 2 |  | M |  | S | Medium | Q1 | Engager team (card content and targeting), BR7 MTU home redesign (shipped FY26). | PM first-pass estimate; to be validated by engineering.
Q2 · #9 | Integrate with the KVouchers platform (IDT vouchers and new flows) | Move eGift onto an IDT voucher that the recipient redeems for a branded card, capturing breakage and improving cash flow and fraud control. Today an eGift purchase issues the branded gift card immediately, so IDT pays the supplier at once and any fraud loss is realised at once. KVouchers issues an IDT voucher first; the recipient redeems it for a specific brand or any brand in the catalogue, and only then is the branded card bought. This delays supplier spend, creates breakage on unredeemed vouchers, gives a consistent branded experience, and adds a fraud checkpoint between purchase and redemption. The platform becomes the foundation of eGift, so the existing purchase flow migrates onto it and the redemption experience is new. | L | 4 |  | M | 2 |  | L |  | M | High | Q2 | KVouchers platform team, Finance (breakage accounting), eGift supplier contracts. | PM first-pass estimate; to be validated by engineering.
Q2 · #10 | Cross-selling MTU on Pinless (module) | Embed the IMTU module in the Pinless calling flow so callers to a number are offered a top-up for that number. Pinless calling knows the number the customer just called. That number is the best possible IMTU lead: the caller cares about the person and the carrier is known from the lookup. This initiative places the module built in Q1 on the post-call screen and the recent-calls list of the BR calling app, offering a single relevant top-up for the called number. Because the module already exists, the work is the host integration, the trigger rules and the analytics. | S | 1 |  | S | 1 |  | S |  | S | High | Q2 | MTU modular component (G1). Calling (Pinless) product team for the host screens. | PM first-pass estimate; to be validated by engineering.
Q2 · #11 | Fraud: integrate the outsourced eGift security layer | Put a specialised fraud vendor in front of every eGift purchase so more good orders are approved and fewer bad ones are paid for. eGift is the most fraud-exposed DCS product because the goods are instant and resellable, and FY26 controls decline a very high share of attempts, much of it issuer declines that no vendor can convert. The vendor handover done in September set the real go-live for March 2027. DCS's work is the integration: device and behavioural signals collected in the app, the vendor decision consumed in the order flow, review outcomes handled, and the results fed back so the model learns. Together with KVouchers, this moves eGift from 'decline everything risky' to 'approve more, hold the risky ones'. | M | 2 |  | S | 1 |  | M |  | NA | Medium | Q2 | Fraud vendor (Accertify, decisioning through IDT Pay), Fraud and Finance teams; vendor go-live planned for March 2027. | PM first-pass estimate; to be validated by engineering.
Q3 · #16 | Request Top-Up (SMS based) | Let a recipient abroad ask a sender for a top-up by SMS, landing the sender in a prefilled purchase flow. Request Top-Up turns the recipient into an acquisition channel. The recipient sends a request from a lightweight web page or by replying to an SMS; the sender receives an SMS with a link that opens the app (or web) with the number, carrier and suggested amount prefilled. Senders who are not BR customers land in onboarding with a RAF credit. The FY26 board carried it as a business spike; FY27 builds it once the RAF loop and the WhatsApp channel exist to amplify it. | M | 2 |  | M | 2 |  | M |  | M | Medium | Q3 | MARCOM (landing page and SMS templates), SMS gateway, RAF platform for the referral hook. | PM first-pass estimate; to be validated by engineering.
Q3 · #17 | eSIM location-based improvements | Use the traveller's location and trip context to recommend, activate and top up the right eSIM plan at the right moment. The eSIM funnel converts 2.3% end to end and loses most users at order review, partly because the customer has to know which region plan they need. Location awareness fixes the recommendation: detect the destination from the device locale, trip dates or arrival, propose the matching regional plan, remind the traveller to install before departure, and offer a data top-up when usage is high in-country. It also positions the eSIM product for the ROW expansion, where the customer is the traveller rather than the sender. | S | 1 |  | M | 2 |  | M |  | S | Medium | Q3 | eSIM supplier (coverage and usage data), OS location permissions. | PM first-pass estimate; to be validated by engineering.
Q4 · #21 | MTU gamification | A cross-product programme of missions, streaks and surprise rewards that drives repeat purchase and product exploration. FY26 shipped the first mechanics as Braze in-app messages: punch cards and first-purchase promos. FY27 turns them into a programme: missions with visible progress, time-limited offers, occasional surprise games, a monthly calendar and sharing of prizes, each targeted to a customer segment. Mechanics and rewards are decided per product. It sits late in the year deliberately so it can pay rewards into the Wallet promo balance and be targeted by Engager rather than by static segments. | M | 2 |  | L | 4 |  | L |  | L | Medium | Q4 | BLS promo engine, Braze in-app messages (FY26 punch cards), Wallet promo balance (B9) for rewards, Loyalty team. | PM first-pass estimate; to be validated by engineering.
Q4 · #22 | Introduce crypto payment checkout | Accept crypto payments for IMTU through Triple-A, settled in fiat, with no crypto custody at IDT. The architecture was defined in July 2026: Triple-A acts as the processor, the customer pays from their own wallet, IDT receives fiat, and IDT Pay gains an adapter so crypto is one more payment method in the order flow. It is a Low priority business goal aimed at a specific segment (crypto-native diaspora in corridors like Nigeria and Venezuela), so it lands in Q4 after the payments work that has broader impact. The Asana subtask to run an education call with Triple-A is the PM entry point. | M | 2 |  | S | 1 |  | M |  | S | Low | Q4 | Triple-A (crypto payment processor), IDT Pay adapter, Legal and Compliance, Finance for fiat settlement. | PM first-pass estimate; to be validated by engineering.
3) Tech Debt and company tech goals |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  |  | <<< 1 FTE >>> S: 1 sprint M: 2 sprints L: 4 sprints XL: 9 sprints XXL: 15 sprints |  |  | Total estimation (BE + APP)
| Company tech goals and tech debt (35% of DCS capacity) | Unit test coverage, service consolidation, transaction-history storage, platform upgrades and the standing company tech goals. Reserved capacity, not scheduled per item. | XL |  |  | XL |  |  | XL | [5 empty] | Reserved capacity (35%), the FY26 convention. Not scheduled per item.
TOTAL demand (initiatives only)
Tech reserve (35%)
Raw capacity: 3 BE and 3 App devs x 26 sprints
Capacity left for initiatives (raw minus reserve)
Over (negative) or under capacity
Sizing scale and colours follow the FY26 sheet:
Source board:

## Timelines
|  | Legend |  | Week 0 = 31 Aug 2026. Sprints are two weeks; S76 is running when the FY opens. PM may start up to 8 weeks before its quarter.
| 1 PM | Discovery, PRD and strategy (PM)
| 1 Designer | Design (Figma)
| 1 TPM | Dev spike, specs and tickets (TPM)
| 3 BE devs | Backend development
| 3 App devs | App development
| 2 QAs | QA and release
| FY26 carry-over | Work in flight when FY27 opens
| Past FY27 | Lands in FY28 at the 35% tech reserve
[17 empty] | 2026 | [17 empty] | 2027 | [51 empty] | 2028
[17 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | FY28 (unfunded at 35% reserve)
[17 empty] | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan
[17 empty] | S76 |  | S77 |  | S78 |  | S79 |  | S80 |  | S81 |  | S82 |  | S83 |  | S84 |  | S85 |  | S86 |  | S87 |  | S88 |  | S89 |  | S90 |  | S91 |  | S92 |  | S93 |  | S94 |  | S95 |  | S96 |  | S97 |  | S98 |  | S99 |  | S100 |  | S101 |  | S102 |  | S103 |  | S104 |  | S105 |  | S106 |  | S107 |  | S108 |  | S109 |  | S110 |  | S111
Goal | Product | Initiative | Priority | Quarter | Status | Size | 1-Pager | PRD | Data | Design | Spike | BE | UI | QA | Team | FTE | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1
FY26 carry-over | MTU | Subscription: BLS promos specific for subscriptions |  | Q1 | In progress | S | [8 empty] | BE | 1 | bar: 36 to 37
[15 empty] | App | 1 | 38: App
[15 empty] | QA | 1 | bar: 40 to 41
FY26 carry-over | MTU | Redesign MTU Home Page (cross-sell) rollout |  | Q1 | In progress | S | [8 empty] | BE
[15 empty] | App | 1 | 36: App
[15 empty] | QA | 1 | bar: 38 to 39
FY26 carry-over | All Products | Cross Sell: success page expiring x-sell deal |  | Q1 | In progress | S | [8 empty] | BE
[15 empty] | App | 1 | 38: App
[15 empty] | QA | 1 | bar: 40
FY26 carry-over | MTU | Improve BE and APP errors presented to users |  | Q1 | In progress | S | [8 empty] | BE | 1 | bar: 36 to 37
[15 empty] | App | 1 | 39: App
[15 empty] | QA | 1 | bar: 41
Business Goal | MTU | #1 Integrate MTU transaction flow to Terminus | High | Q1 | Carry over | M | - | - | - | - | - | - | - | - | PM
|  | 14 Sep 2026 to 18 Oct 2026 | [12 empty] | Dsgn
|  | BE M (1 FTE spr) · App - (0 FTE spr) · Design - | [12 empty] | TPM
[15 empty] | BE | 1 | bar: 38 to 39
App
QA | bar: 42
Business Goal | MTU | #2 New Channel: roll out the WhatsApp MTU chatbot | High | Q1 | Carry over | M | [8 empty] | PM | bar: 36
|  | 31 Aug 2026 to 25 Oct 2026 | [12 empty] | Dsgn
|  | BE M (2 FTE spr) · App - (0 FTE spr) · Design - | [12 empty] | TPM |  | 37: TPM
[15 empty] | BE | 1 | bar: 38 to 41
App
QA | bar: 42 to 43
Board Goal | MTU | #3 Introduce postpaid top-ups (direct billers) | High | Q1 | Planned | L | [8 empty] | PM | bar: 36 to 37
|  | 31 Aug 2026 to 6 Dec 2026 | [12 empty] | Dsgn |  | 38: Dsgn
|  | BE L (4 FTE spr) · App S (1 FTE spr) · Design S | [12 empty] | TPM |  | 40: TPM
[15 empty] | BE | 2 | bar: 42 to 45
[15 empty] | App | 1 | 46: App
QA | bar: 48 to 49
Business Goal | MTU | #4 MTU modular component and cross-selling MTU on Money Transfer | High | Q1 | Planned | L | [8 empty] | PM | bar: 37 to 38
|  | 7 Sep 2026 to 17 Jan 2027 | [12 empty] | Dsgn |  | 39: Dsgn
|  | BE M (2 FTE spr) · App L (4 FTE spr) · Design M | [12 empty] | TPM |  | 42: TPM
[15 empty] | BE | 1 | bar: 46 to 49
[15 empty] | App | 2 | 50: App
QA | bar: 1 to 2
Board Goal | MTU | #5 Reduce subscription cancellations | High | Q1 | Planned | L | [8 empty] | PM | bar: 38 to 40
|  | 14 Sep 2026 to 14 Feb 2027 | [12 empty] | Dsgn |  | 41: Dsgn
|  | BE M (2 FTE spr) · App L (4 FTE spr) · Design M | [12 empty] | TPM |  | 44: TPM
[15 empty] | BE | 1 | bar: 46 to 49
[15 empty] | App | 2 | 1: App
QA | bar: 5 to 6
Business Goal | MTU | #6 Cross-sell 2.0: Engager cards on the MTU home page | Medium | Q1 | Planned | M | [8 empty] | PM | bar: 39 to 40
|  | 21 Sep 2026 to 7 Mar 2027 | [12 empty] | Dsgn |  | 42: Dsgn
|  | BE S (1 FTE spr) · App M (2 FTE spr) · Design S | [12 empty] | TPM |  | 44: TPM
[15 empty] | BE | 1 | bar: 50 to 51
[15 empty] | App | 1 | 5: App
QA | bar: 9
Board Goal | All Products | #7 Add mobile payments (Apple Pay and Google Pay) | High | Q2 | Planned | L | [8 empty] | PM | bar: 41 to 42
|  | 5 Oct 2026 to 18 Apr 2027 | [12 empty] | Dsgn |  | 44: Dsgn
|  | BE L (4 FTE spr) · App L (4 FTE spr) · Design S | [12 empty] | TPM |  | 46: TPM
[15 empty] | BE | 2 | bar: 52 to 2
[15 empty] | App | 2 | 9: App
QA | bar: 13 to 15
Board Goal | MTU | #8 Deploy AI-powered dynamic pricing (offer price and variable fees) | High | Q2 | Planned | M | [8 empty] | PM | bar: 41 to 43
|  | 5 Oct 2026 to 25 Apr 2027 | [12 empty] | Dsgn |  | 44: Dsgn
|  | BE M (2 FTE spr) · App S (1 FTE spr) · Design S | [12 empty] | TPM |  | 46: TPM
[15 empty] | BE | 1 | bar: 3 to 6
[15 empty] | App | 1 | 13: App
QA | bar: 15 to 16
Business Goal | eGIFT | #9 Integrate with the KVouchers platform (IDT vouchers and new flows) | High | Q2 | Planned | L | [8 empty] | PM | bar: 43 to 45
|  | 19 Oct 2026 to 9 May 2027 | [12 empty] | Dsgn |  | 46: Dsgn
|  | BE L (4 FTE spr) · App M (2 FTE spr) · Design M | [12 empty] | TPM |  | 49: TPM
[15 empty] | BE | 2 | bar: 7 to 10
[15 empty] | App | 1 | 13: App
QA | bar: 17 to 18
Business Goal | MTU | #10 Cross-selling MTU on Pinless (module) | High | Q2 | Planned | S | [8 empty] | PM | bar: 44
|  | 26 Oct 2026 to 2 May 2027 | [12 empty] | Dsgn |  | 46: Dsgn
|  | BE S (1 FTE spr) · App S (1 FTE spr) · Design S | [12 empty] | TPM |  | 48: TPM
[15 empty] | BE | 1 | bar: 11 to 12
[15 empty] | App | 1 | 15: App
QA | bar: 17
Business Goal | eGIFT | #11 Fraud: integrate the outsourced eGift security layer | Medium | Q2 | Planned | M | [8 empty] | PM | bar: 45 to 46
|  | 2 Nov 2026 to 23 May 2027 | [12 empty] | Dsgn
|  | BE M (2 FTE spr) · App S (1 FTE spr) · Design - | [12 empty] | TPM |  | 49: TPM
[15 empty] | BE | 1 | bar: 11 to 14
[15 empty] | App | 1 | 17: App
QA | bar: 19 to 20
Board Goal | MTU | #12 Support sponsor calling plans and cross-sell them in the IMTU flow | High | Q2 | Planned | M | [8 empty] | PM | bar: 46 to 47
|  | 9 Nov 2026 to 6 Jun 2027 | [12 empty] | Dsgn |  | 48: Dsgn
|  | BE M (2 FTE spr) · App M (2 FTE spr) · Design S | [12 empty] | TPM |  | 50: TPM
[15 empty] | BE | 1 | bar: 13 to 16
[15 empty] | App | 1 | 17: App
QA | bar: 21 to 22
Board Goal | All Products | #13 Introduce bundling capabilities for DTC | High | Q3 | Planned | XL | [8 empty] | PM | bar: 1 to 4
|  | 4 Jan 2027 to 15 Aug 2027 | [12 empty] | Dsgn |  | 5: Dsgn
|  | BE XL (9 FTE spr) · App L (4 FTE spr) · Design L | [12 empty] | TPM |  | 9: TPM
[15 empty] | BE | 2 | bar: 17 to 25
[15 empty] | App | 2 | 26: App
QA | bar: 30 to 32
Board Goal | All Products | #14 Expand the BR app in ROW markets (Pinless, IMTU and eSIM) | High | Q3 | FY28 risk | L | [8 empty] | PM | bar: 1 to 4
|  | 4 Jan 2027 to 12 Sep 2027 | [12 empty] | Dsgn |  | 5: Dsgn
|  | BE L (4 FTE spr) · App L (4 FTE spr) · Design M | [12 empty] | TPM |  | 8: TPM
[15 empty] | BE | 2 | bar: 26 to 29
[15 empty] | App | 2 | 30: App
QA | bar: 34 to 36
Board Goal | All Products | #15 Support the RAF program with a fully trackable journey | Medium | Q3 | FY28 risk | M | [8 empty] | PM | bar: 5 to 6
|  | 1 Feb 2027 to 3 Oct 2027 | [12 empty] | Dsgn |  | 8: Dsgn
|  | BE M (2 FTE spr) · App M (2 FTE spr) · Design S | [12 empty] | TPM |  | 10: TPM
[15 empty] | BE | 1 | bar: 30 to 33
[15 empty] | App | 1 | 34: App
QA | bar: 38 to 39
Business Goal | MTU | #16 Request Top-Up (SMS based) | Medium | Q3 | FY28 risk | M | [8 empty] | PM | bar: 5 to 6
|  | 1 Feb 2027 to 3 Oct 2027 | [12 empty] | Dsgn |  | 9: Dsgn
|  | BE M (2 FTE spr) · App M (2 FTE spr) · Design M | [12 empty] | TPM |  | 12: TPM
[15 empty] | BE | 1 | bar: 30 to 33
[15 empty] | App | 1 | 34: App
QA | bar: 38 to 39
Business Goal | eSIM | #17 eSIM location-based improvements | Medium | Q3 | FY28 risk | M | [8 empty] | PM | bar: 7 to 8
|  | 15 Feb 2027 to 31 Oct 2027 | [12 empty] | Dsgn |  | 10: Dsgn
|  | BE S (1 FTE spr) · App M (2 FTE spr) · Design S | [12 empty] | TPM |  | 12: TPM
[15 empty] | BE | 1 | bar: 34 to 35
[15 empty] | App | 1 | 38: App
QA | bar: 42 to 43
Board Goal | All Products | #18 Personalised experiences via Engager (ML-driven) | Medium | Q4 | FY28 risk | M | [8 empty] | PM | bar: 14 to 16
|  | 5 Apr 2027 to 31 Oct 2027 | [12 empty] | Dsgn |  | 17: Dsgn
|  | BE M (2 FTE spr) · App M (2 FTE spr) · Design M | [12 empty] | TPM |  | 20: TPM
[15 empty] | BE | 1 | bar: 34 to 37
[15 empty] | App | 1 | 38: App
QA | bar: 42 to 43
Board Goal | All Products | #19 Promo balances support for the BR Wallet | Medium | Q4 | FY28 risk | L | [8 empty] | PM | bar: 14 to 15
|  | 5 Apr 2027 to 28 Nov 2027 | [12 empty] | Dsgn |  | 16: Dsgn
|  | BE L (4 FTE spr) · App M (2 FTE spr) · Design S | [12 empty] | TPM |  | 18: TPM
[15 empty] | BE | 2 | bar: 38 to 41
[15 empty] | App | 1 | 42: App
QA | bar: 46 to 47
Board Goal | MTU | #20 Support the IVA migration for MTU | Medium | Q4 | FY28 risk | M | [8 empty] | PM | bar: 16 to 17
|  | 19 Apr 2027 to 28 Nov 2027 | [12 empty] | Dsgn
|  | BE M (2 FTE spr) · App - (0 FTE spr) · Design - | [12 empty] | TPM |  | 20: TPM
[15 empty] | BE | 1 | bar: 42 to 45
App
QA | bar: 46 to 47
Business Goal | All Products | #21 MTU gamification | Medium | Q4 | FY28 risk | L | [8 empty] | PM | bar: 17 to 19
|  | 26 Apr 2027 to 26 Dec 2027 | [12 empty] | Dsgn |  | 20: Dsgn
|  | BE M (2 FTE spr) · App L (4 FTE spr) · Design L | [12 empty] | TPM |  | 24: TPM
[15 empty] | BE | 1 | bar: 42 to 45
[15 empty] | App | 2 | 46: App
QA | bar: 50 to 51
Business Goal | MTU | #22 Introduce crypto payment checkout | Low | Q4 | FY28 risk | M | [8 empty] | PM | bar: 18 to 19
|  | 3 May 2027 to 9 Jan 2028 | [12 empty] | Dsgn |  | 20: Dsgn
|  | BE M (2 FTE spr) · App S (1 FTE spr) · Design S | [12 empty] | TPM |  | 22: TPM
[15 empty] | BE | 1 | bar: 46 to 49
[15 empty] | App | 1 | 50: App
QA | bar: 52 to 1

## Sequence
Order | Id | Initiative | Goal | Product | Priority | Quarter | BE size | BE FTE sprints | App size | App FTE sprints | Design | Start | End | Status | PM start | Design start | TPM start | BE start | App start | QA start | PM end | Design end | TPM end | BE end | App end | QA end | Dependencies | Asana
1 | G6 | Integrate MTU transaction flow to Terminus | Business Goal | MTU | High | Q1 | M | 1 | - | 0 | - | 2026-09-14 | 2026-10-19 | Fits in FY27 |  |  |  | 2026-09-14 |  | 2026-10-12 |  |  |  | 2026-09-28 |  | 2026-10-19 | Terminus team (fraud platform). Carry-over from FY26, backend In Progress.
2 | G4 | New Channel: roll out the WhatsApp MTU chatbot | Business Goal | MTU | High | Q1 | M | 2 | - | 0 | - | 2026-08-31 | 2026-10-26 | Fits in FY27 | 2026-08-31 |  | 2026-09-07 | 2026-09-14 |  | 2026-10-12 | 2026-09-07 |  | 2026-09-14 | 2026-10-12 |  | 2026-10-26 | WhatsApp Business team (chatbot and conversation design), DTC Universal API (shipped FY26), MARCOM for the entry deep link.
3 | B11 | Introduce postpaid top-ups (direct billers) | Board Goal | MTU | High | Q1 | L | 4 | S | 1 | S | 2026-08-31 | 2026-12-07 | Fits in FY27 | 2026-08-31 | 2026-09-14 | 2026-09-28 | 2026-10-12 | 2026-11-09 | 2026-11-23 | 2026-09-14 | 2026-09-28 | 2026-10-12 | 2026-11-09 | 2026-11-23 | 2026-12-07 | K2 connectors team (biller integration), Tigo and other carriers for postpaid APIs, Finance for non-instant settlement.
4 | G1 | MTU modular component and cross-selling MTU on Money Transfer | Business Goal | MTU | High | Q1 | M | 2 | L | 4 | M | 2026-09-07 | 2027-01-18 | Fits in FY27 | 2026-09-07 | 2026-09-21 | 2026-10-12 | 2026-11-09 | 2026-12-07 | 2027-01-04 | 2026-09-21 | 2026-10-12 | 2026-10-26 | 2026-12-07 | 2027-01-04 | 2027-01-18 | Boss Money app team (host surface), Engager for offer selection. Spec started in Confluence (Modular IMTU Component).
5 | B2 | Reduce subscription cancellations | Board Goal | MTU | High | Q1 | M | 2 | L | 4 | M | 2026-09-14 | 2027-02-15 | Fits in FY27 | 2026-09-14 | 2026-10-05 | 2026-10-26 | 2026-11-09 | 2027-01-04 | 2027-02-01 | 2026-10-05 | 2026-10-26 | 2026-11-09 | 2026-12-07 | 2027-02-01 | 2027-02-15 | Subly (subscription engine), CRM for the Braze savings attribute, Amplitude taxonomy fixes (DCS-5331 style) for the cancel funnel.
6 | G3 | Cross-sell 2.0: Engager cards on the MTU home page | Business Goal | MTU | Medium | Q1 | S | 1 | M | 2 | S | 2026-09-21 | 2027-03-08 | Fits in FY27 | 2026-09-21 | 2026-10-12 | 2026-10-26 | 2026-12-07 | 2027-02-01 | 2027-03-01 | 2026-10-05 | 2026-10-26 | 2026-11-02 | 2026-12-21 | 2027-03-01 | 2027-03-08 | Engager team (card content and targeting), BR7 MTU home redesign (shipped FY26).
7 | B4 | Add mobile payments (Apple Pay and Google Pay) | Board Goal | All Products | High | Q2 | L | 4 | L | 4 | S | 2026-10-05 | 2027-04-19 | Fits in FY27 | 2026-10-05 | 2026-10-26 | 2026-11-09 | 2026-12-21 | 2027-03-01 | 2027-03-29 | 2026-10-19 | 2026-11-09 | 2026-11-23 | 2027-01-18 | 2027-03-29 | 2027-04-19 | IDT Pay (tokenisation and processor support), Fraud team (Apple Pay fraud at 0.01%), Apple and Google merchant onboarding.
8 | B1 | Deploy AI-powered dynamic pricing (offer price and variable fees) | Board Goal | MTU | High | Q2 | M | 2 | S | 1 | S | 2026-10-05 | 2027-04-26 | Fits in FY27 | 2026-10-05 | 2026-10-26 | 2026-11-09 | 2027-01-18 | 2027-03-29 | 2027-04-12 | 2026-10-26 | 2026-11-09 | 2026-11-23 | 2027-02-15 | 2027-04-12 | 2027-04-26 | Pricing team and OMTU (pricing model and service), K2 (price and fee fields), Legal for price display rules.
9 | G9 | Integrate with the KVouchers platform (IDT vouchers and new flows) | Business Goal | eGIFT | High | Q2 | L | 4 | M | 2 | M | 2026-10-19 | 2027-05-10 | Fits in FY27 | 2026-10-19 | 2026-11-09 | 2026-11-30 | 2027-02-15 | 2027-03-29 | 2027-04-26 | 2026-11-09 | 2026-11-30 | 2026-12-14 | 2027-03-15 | 2027-04-26 | 2027-05-10 | KVouchers platform team, Finance (breakage accounting), eGift supplier contracts.
10 | G2 | Cross-selling MTU on Pinless (module) | Business Goal | MTU | High | Q2 | S | 1 | S | 1 | S | 2026-10-26 | 2027-05-03 | Fits in FY27 | 2026-10-26 | 2026-11-09 | 2026-11-23 | 2027-03-15 | 2027-04-12 | 2027-04-26 | 2026-11-02 | 2026-11-23 | 2026-11-30 | 2027-03-29 | 2027-04-26 | 2027-05-03 | MTU modular component (G1). Calling (Pinless) product team for the host screens.
11 | G10 | Fraud: integrate the outsourced eGift security layer | Business Goal | eGIFT | Medium | Q2 | M | 2 | S | 1 | - | 2026-11-02 | 2027-05-24 | Fits in FY27 | 2026-11-02 |  | 2026-11-30 | 2027-03-15 | 2027-04-26 | 2027-05-10 | 2026-11-16 |  | 2026-12-07 | 2027-04-12 | 2027-05-10 | 2027-05-24 | Fraud vendor (Accertify, decisioning through IDT Pay), Fraud and Finance teams; vendor go-live planned for March 2027.
12 | B7 | Support sponsor calling plans and cross-sell them in the IMTU flow | Board Goal | MTU | High | Q2 | M | 2 | M | 2 | S | 2026-11-09 | 2027-06-07 | Fits in FY27 | 2026-11-09 | 2026-11-23 | 2026-12-07 | 2027-03-29 | 2027-04-26 | 2027-05-24 | 2026-11-23 | 2026-12-07 | 2026-12-14 | 2027-04-26 | 2027-05-24 | 2027-06-07 | Calling plans product team (sponsor plan catalogue and provisioning), Engager for offer placement.
13 | B10 | Introduce bundling capabilities for DTC | Board Goal | All Products | High | Q3 | XL | 9 | L | 4 | L | 2027-01-04 | 2027-08-16 | Fits in FY27 | 2027-01-04 | 2027-02-01 | 2027-03-01 | 2027-04-26 | 2027-06-28 | 2027-07-26 | 2027-02-01 | 2027-03-01 | 2027-03-22 | 2027-06-28 | 2027-07-26 | 2027-08-16 | K2 catalogue and order services, IDT Pay (single charge, partial refunds), Finance for revenue split, product teams for bundle definitions.
14 | B8 | Expand the BR app in ROW markets (Pinless, IMTU and eSIM) | Board Goal | All Products | High | Q3 | L | 4 | L | 4 | M | 2027-01-04 | 2027-09-13 | Lands in FY28 at 35% reserve | 2027-01-04 | 2027-02-01 | 2027-02-22 | 2027-06-28 | 2027-07-26 | 2027-08-23 | 2027-02-01 | 2027-02-22 | 2027-03-08 | 2027-07-26 | 2027-08-23 | 2027-09-13 | Country launch programme (legal, tax, payments per market), IDT Pay local payment methods, Calling (Pinless) team, K2 offer catalogue per market.
15 | B5 | Support the RAF program with a fully trackable journey | Board Goal | All Products | Medium | Q3 | M | 2 | M | 2 | S | 2027-02-01 | 2027-10-04 | Lands in FY28 at 35% reserve | 2027-02-01 | 2027-02-22 | 2027-03-08 | 2027-07-26 | 2027-08-23 | 2027-09-20 | 2027-02-15 | 2027-03-08 | 2027-03-22 | 2027-08-23 | 2027-09-20 | 2027-10-04 | DTC Core (RAF platform, shipped FY26), CRM for reward messaging, Data team for attribution reporting.
16 | G7 | Request Top-Up (SMS based) | Business Goal | MTU | Medium | Q3 | M | 2 | M | 2 | M | 2027-02-01 | 2027-10-04 | Lands in FY28 at 35% reserve | 2027-02-01 | 2027-03-01 | 2027-03-22 | 2027-07-26 | 2027-08-23 | 2027-09-20 | 2027-02-15 | 2027-03-22 | 2027-04-05 | 2027-08-23 | 2027-09-20 | 2027-10-04 | MARCOM (landing page and SMS templates), SMS gateway, RAF platform for the referral hook.
17 | G11 | eSIM location-based improvements | Business Goal | eSIM | Medium | Q3 | S | 1 | M | 2 | S | 2027-02-15 | 2027-11-01 | Lands in FY28 at 35% reserve | 2027-02-15 | 2027-03-08 | 2027-03-22 | 2027-08-23 | 2027-09-20 | 2027-10-18 | 2027-03-01 | 2027-03-22 | 2027-03-29 | 2027-09-06 | 2027-10-18 | 2027-11-01 | eSIM supplier (coverage and usage data), OS location permissions.
18 | B6 | Personalised experiences via Engager (ML-driven) | Board Goal | All Products | Medium | Q4 | M | 2 | M | 2 | M | 2027-04-05 | 2027-11-01 | Lands in FY28 at 35% reserve | 2027-04-05 | 2027-04-26 | 2027-05-17 | 2027-08-23 | 2027-09-20 | 2027-10-18 | 2027-04-26 | 2027-05-17 | 2027-05-31 | 2027-09-20 | 2027-10-18 | 2027-11-01 | Engager and Data Science teams (ML models and next-best-offer), CRM (Braze), G3 Engager cards as the delivery surface.
19 | B9 | Promo balances support for the BR Wallet | Board Goal | All Products | Medium | Q4 | L | 4 | M | 2 | S | 2027-04-05 | 2027-11-29 | Lands in FY28 at 35% reserve | 2027-04-05 | 2027-04-19 | 2027-05-03 | 2027-09-20 | 2027-10-18 | 2027-11-15 | 2027-04-19 | 2027-05-03 | 2027-05-17 | 2027-10-18 | 2027-11-15 | 2027-11-29 | BR Wallet team (balance types and ledger), BLS promo engine, Boss Money app team, Finance for promo liability.
20 | B3 | Support the IVA migration for MTU | Board Goal | MTU | Medium | Q4 | M | 2 | - | 0 | - | 2027-04-19 | 2027-11-29 | Lands in FY28 at 35% reserve | 2027-04-19 |  | 2027-05-17 | 2027-10-18 |  | 2027-11-15 | 2027-05-03 |  | 2027-05-31 | 2027-11-15 |  | 2027-11-29 | IVA (Intelligent Virtual Agent) programme team, CSA and IVR teams, DTC Universal API (CSA connector shipped FY26).
21 | G8 | MTU gamification | Business Goal | All Products | Medium | Q4 | M | 2 | L | 4 | L | 2027-04-26 | 2027-12-27 | Lands in FY28 at 35% reserve | 2027-04-26 | 2027-05-17 | 2027-06-14 | 2027-10-18 | 2027-11-15 | 2027-12-13 | 2027-05-17 | 2027-06-14 | 2027-06-28 | 2027-11-15 | 2027-12-13 | 2027-12-27 | BLS promo engine, Braze in-app messages (FY26 punch cards), Wallet promo balance (B9) for rewards, Loyalty team.
22 | G5 | Introduce crypto payment checkout | Business Goal | MTU | Low | Q4 | M | 2 | S | 1 | S | 2027-05-03 | 2028-01-10 | Lands in FY28 at 35% reserve | 2027-05-03 | 2027-05-17 | 2027-05-31 | 2027-11-15 | 2027-12-13 | 2027-12-27 | 2027-05-17 | 2027-05-31 | 2027-06-07 | 2027-12-13 | 2027-12-27 | 2028-01-10 | Triple-A (crypto payment processor), IDT Pay adapter, Legal and Compliance, Finance for fiat settlement.

## Capacity
Role | People | Parallel lanes used by the plan | Note
PM | 1 | 2 | one PM runs two discovery tracks at a time
Design | 1 | 2 | one designer runs two initiatives at a time, as in FY26
TPM | 1 | 2 | spikes and ticket breakdown for two initiatives at a time
BE | 3 | 2 | 35% reserved for tech debt and company tech goals, leaving 2 lanes for initiatives
App | 3 | 2 | 35% reserved for tech debt and company tech goals, leaving 2 lanes for initiatives
QA | 2 | 2
Assumption | Value
Fiscal year | 31 Aug 2026 to 29 Aug 2027
Sprint length | 2 weeks; S76 runs when the FY opens, S101 is the last full FY27 sprint
Tech reserve | 35% of BE and App capacity, as in FY26
Sizing scale | S 1, M 2, L 4, XL 9 FTE sprints (FY26 scale)
Phase order | PM, Design, TPM, BE, App, QA in strict sequence per initiative
Hand-off rule | a role that finishes an initiative starts the next one the following week
PM lead | PM may start up to 8 weeks before the initiative's target quarter
Estimates | PM first pass, to be validated by engineering in the Comments column